## 110_12L
110-12
2020-10-20
POLLUTION PREVENTION PLAN
This project is regulated by the requirements of the Iowa Department of Natural Resources (DNR) National Pollutant Discharge Elimination
System (NPDES) General Permit No. 2 OR an Iowa Department of Natural Resources (DNR) National Pollutant Discharge Elimination System
(NPDES) individual storm water permit. The Contractor shall carry out the terms and conditions of this permit and the Pollution
Prevention Plan (PPP).
This Base PPP includes information on Roles and Responsibilities, Project Site Description, Controls, Maintenance Procedures, Inspection
Requirements, Non-Storm Water Controls, Potential Sources of Off Right-of-Way Pollution, and Definitions. This plan references other
documents rather than repeating the information contained in the documents. A copy of this Base Pollution Prevention Plan, amended as
needed during construction, will be readily available for review.
All contractors shall conduct their operations in a manner that controls pollutants, minimizes erosion, and prevents sediments from
entering waters of the state and leaving the highway right-of-way. The Contractor shall be responsible for compliance and
implementation of the PPP for their entire contract. This responsibility shall be further shared with subcontractors whose work is a
source of potential pollution as defined in this PPP.
I. ROLES AND RESPONSIBILITES
A. Designer:
1. Prepares Base PPP included in the project plan.
2. Prepares Notice of Intent (NOI) submitted to Iowa DNR.
3. Is signature authority on the Base PPP. If consultant designed, signature from Contracting Authority is also required.
B. Contractor:
1. Signs a co-permittee certification statement adhering to the requirements of the NPDES permit and this PPP. All co-permittees
are legally required under the Clean Water Act and the Iowa Administrative Code to ensure compliance with the terms and
conditions of this PPP.
2. Designates a Water Pollution Control Manager (WPCM), who has the duties and responsibilities as defined in Section 2602 of the
Standard Specifications.
3. Submits an Erosion Control Implementation Plan (ECIP) and ECIP updates according to Section 2602 of the Standard Specifications.
4. Installs and maintains appropriate controls. This work may be subcontracted as documented through Subcontractor Request Forms
(Form 830231).
5. Supervises and implements good housekeeping practices according to Paragraph III, C, 2.
6. Conducts joint required inspections of the site with inspection staff. When Contractor is not mobilized on site,
Contractor may delegate this responsibility to a trained or certified subcontractor. Contracting Authority also may waive
joint inspection requirement during winter shutdown. In both circumstances, WPCM (or trained or certified delegate from
the Contractor) is still responsible to review and sign inspection reports.
7. Complies with training and certification requirements of Section 2602 of the Standard Specifications.
8. Submits amended PPP site map according to Section 2602 of the Standard Specifications.
C. Subcontractors:
1. Sign a co-permittee certification statement adhering to the requirements of the NPDES permit and this PPP if: responsible for
sediment or erosion controls; involved in land disturbing activities; or performing work that is a source of potential pollution
as defined in this PPP. Subcontracted work items are identified in Subcontractor Request Forms (Form 830231). All
co-permittees are legally required under the Clean Water Act and the Iowa Administrative Code to ensure compliance with the
terms and conditions of this PPP.
2. Implement good housekeeping practices according to Paragraph III, C, 2.
D. RCE/Project Engineer:
1. Is Project Storm Water Manager.
2. On projects where DOT is the Contracting Authority, is current with erosion control training or certification.
3. Takes actions necessary to ensure compliance with storm water requirements including, where appropriate, issuing stop work
orders, and directing additional inspections at construction project sites that are experiencing problems with achieving permit
compliance.
4. Orders the taking of measures to cease, correct, prevent, or minimize the consequences of non-compliance with the storm water
requirements of the Applicable Permit.
5. Supervises all work necessary to meet storm water requirements at the Project, including work performed by contractors and
subcontractors.
6. Requires employees, contractors, and subcontractors to take appropriate responsive action to comply with storm water
requirements, including requiring any such person to cease or correct a violation of storm water requirements, and to order or
recommend such other actions as necessary to meet storm water requirements.
7. Is familiar with the Project PPP and storm water site map.
8. On projects where DOT is Contracting Authority, is responsible for periodically monitoring inspection reports to
determine whether deficiencies identified in inspection reports were adequately and timely addressed, and if not, has the
authority and responsibility to direct immediate actions to correct the deficiencies.
9. Is the point of contact for the Project for regulatory officials, Inspector, contractors, and subcontractors regarding storm
water requirements.
10. Is signature authority on Notice of Discontinuation.
11. Maintains an up-to-date record of contractors, subcontractors, and subcontracted work items through Subcontractor Request Forms
(Form 830231).
12. Makes information to determine permit compliance available to the DNR upon their request.
E. Inspector:
1. Updates PPP through fieldbook entries and storm water site inspection reports if there is a change in design, construction,
operation, or maintenance which has a significant effect on the discharge of pollutants from the project.
2. Makes information to determine permit compliance available to the DNR upon their request.
3. Conducts joint required inspections of the site with the contractor/subcontractor.
4. Completes an inspection report after each inspection.
5. Is signature authority on storm water inspection reports.
II. PROJECT SITE DESCRIPTION
A. This Pollution Prevention Plan (PPP) is for the construction of the rest area along northbound I-29 near Onawa, in Monona County.
B. This PPP covers approximately 11.9 acres with an estimated 9.5 acres being disturbed.
The portion of the PPP covered by this contract has 9.5 acres disturbed. | EDIT II for current project and update other text to match Onawa
C. The PPP is located in an area of (14) soil association (Albaton - Luton - Onawa). The estimated weighted average runoff | Second number includes seeding
coefficient number for this PPP after completion will be 0.38. | first number includes are between parking and ML
D. Storm Water Site Map - Multiple sources of information comprise the base storm water site map including:
1. Drainage Patterns – Plan and Profile sheets and Situation plans.
2. Proposed Slopes – Cross Sections.
3. Areas of Soil Disturbance – Construction limits shown on Plan and Profile sheets.
4. Location of Structural Controls – Tabulations in C sheets.
5. Locations of Non-structural Controls – Tabulations in C sheets.
6. Locations of Stabilization Practices – Generally within construction limits shown on Plan and Profile sheets.
7. Surface Waters (including wetlands) – Project Location Map and Plan and Profile sheets.
8. Locations where Storm Water is Discharged – Plan and Profile sheets.
E. The base storm water site map is amended by contract modifications and progress payments (fieldbook entries) of completed erosion
control work. Also, due to project phasing, erosion and sediment controls shown on project plans may not be installed until
needed, based on site conditions. For example, silt fence ditch checks will typically not be installed until the ditch has been
installed. Installed locations may also be modified from tabulation locations by field staff. Installed locations will be
documented by fieldbook entries and amended PPP site map.
F. Runoff from this work will flow into roadside ditches that will carry the flow to Guard Lake.
III. CONTROLS
A. The Contractor’s ECIP specified in Article 2602.03 of the Standard Specifications for accomplishment of storm water controls should
clearly describe the intended sequence of major activities, and for each activity define the control measure and the timing during
the construction process that the measure will be implemented.
B. Preserve vegetation in areas not needed for construction.
C. Sections 2601 and 2602 of the Standard Specifications define requirements to implement erosion and sediment control measures.
Actual quantities used and installed locations may vary from the Base PPP and amendment of the plan will be documented via
fieldbook entries, amended PPP site map, or by contract modification. Additional erosion and sediment control items may be
required as determined by the inspector and/or contractor during storm water site inspections. If the work involved is not
applicable to any contract items, the work will be paid for according to Article 1109.03 paragraph B of the Standard
Specifications.
1. EROSION AND SEDIMENT CONTROLS
a. Stabilization Practices
1) Site plans will ensure that existing vegetation or natural buffers are preserved where attainable and disturbed portions
of the site will be stabilized.
2) Initialize stabilization of disturbed areas immediately after clearing, grading, excavating, or other earth disturbing
activities have:
a) Permanently ceased on any portion of the site, or
b) Temporarily ceased on any portion of the site and will not resume for a period exceeding 14 calendar days.
3) Staged permanent and/or temporary stabilizing seeding and mulching shall be completed as the disturbed areas are
completed. Incomplete areas shall be stabilized according to paragraph III, C, 1, a, 2, b above.
4) Permanent and Temporary Stabilization practices to be used for this project are located in the Estimated Project
Quantities (100-0A, 100-1A, or 100-1C) and Estimate Reference Information (100-4A) located in the C sheets. Typical
drawings detailing construction of the practices to be used on this project are referenced in the Standard Road
Plans Tabulation (105-4) in the C sheets.
5) Preservation of existing vegetation within right-of-way or easements will act as vegetative buffer strips.
6) Preservation of topsoil: Bid items to be used for this project are located in the Estimated Project Quantities (100-0A,
100-1A, or 100-1C) and Estimate Reference Information (100-4A) located in the C sheets. Additional information may be
found in Tabulations in the C or T sheets or is referenced in Section 2105 of Standard Specifications.
b. Structural Practices
1) Structural practices will be implemented to divert flows from exposed soils and detain or otherwise limit runoff and the
discharge of pollutants from exposed areas of the site. Additionally, structural practices may include: silt basins that
provide 3600 cubic feet of storage per acre drained or equivalent sediment controls, outlet structures that withdraw water
from surface when discharging basins, and controls to direct storm water to vegetated areas.
2) Structural practices to be used for this project are located in the Estimated Project Quantities (100-0A, 100-1A, or
100-1C) and Estimate Reference Information (100-4A) located in the C sheets, as well as all other item specific
Tabulations. Typical drawings detailing construction of the devices to be used on this project can be found in the B
sheets or are referenced in the Standard Road Plans Tabulation (105-4) located in the C sheets.
c. Storm Water Management
Measures shall be installed during the construction process to control pollutants in storm water discharges that will occur
after construction operations have been completed. This may include velocity dissipation devices at discharge locations and
along length of outfall channel as necessary to provide a non-erosion velocity flow from structure to water course. If
included with this project, these items are located in the Estimated Project Quantities (100-0A, 100-1A, or 100-1C) and
Estimate Reference Information (100-4A) located in the C sheets, as well as all other item specific Tabulations. Typical
drawings detailing construction of the practices to be used on this project are referenced in the Standard Road Plans
Tabulation (105-4) in the C sheets. The installation of these devices may be subject to Section 404 of the Clean Water Act.
2. OTHER CONTROLS
Contractor disposal of unused construction materials and construction material wastes shall comply with applicable state and
local waste disposal, sanitary sewer, or septic system regulations. In the event of a conflict with other governmental laws,
rules and regulations, the more restrictive applicable laws, rules or regulations shall apply.
a. Vehicle Entrances and Exits - Construct and maintain entrances and exits to prevent tracking of sediments onto roadways.
b. Material Delivery, Storage and Use - Implement practices to prevent discharge of construction materials during delivery,
storage, and use.
c. Stockpile Management - Install controls to reduce or eliminate pollution of storm water from stockpiles of soil and paving.
d. Waste Disposal - Do not discharge any materials, including building materials, into waters of the state, except as
authorized by a Section 404 permit.
e. Spill Prevention and Control - Implement chemical spill and leak prevention and response procedures to contain and clean up
spills and prevent material discharges to the storm drain system and waters of the state.
f. Concrete Residuals and Washout Wastes - Waste shall not be discharged to a surface water and is not allowed to adversely
affect a water of the state. Designate temporary concrete washout facilities for rinsing out concrete trucks. Provide
directions to truck drivers where designated washout facilities are located. Designated washout areas should be
located at least 50 feet away from storm drains, streams or other water bodies. Care should be taken to ensure these
facilities do not overflow during storm events.
g. Concrete Grooving/Grinding Slurry – Do not discharge slurry to a waterbody or storm drain. Slurry may be applied on
foreslopes or removed from the project.
h. Vehicle and Equipment Storage and Maintenance Areas - Perform on site fueling and maintenance in accordance with all
environment laws such as proper storage of onsite fuels and proper disposal of used engine oil or other fluids on site.
Employ washing practices that prevent contamination of surface and ground water from wash water. Wash waters must be
treated in a sediment basin or alternative control that provides equivalent or better treatment prior to discharge.
i. Litter Management - Ensure employees properly dispose of litter. Minimize exposure of trash if exposure to precipitation or
storm water would result in a discharge of pollutants.
j. Dewatering – Properly treat water to remove suspended sediment before it re-enters a waterbody or discharges off-site.
Measures are also to be taken to prevent scour erosion at dewatering discharge point.
3. APPROVED STATE OR LOCAL PLANS
During the course of this construction, it is possible that situations will arise where unknown materials will be encountered.
When such situations are encountered, they will be handled according to all federal, state, and local regulations in effect at
the time.
IV. MAINTENANCE PROCEDURES
The Contractor is required to maintain all temporary erosion and sediment control measures in proper working order, including
cleaning, repairing, or replacing them throughout the contract period. This shall begin when the features have lost 50% of their
capacity.
V. INSPECTION REQUIREMENTS
A. Inspections shall be made jointly by the Contractor and the Contracting Authority's inspector at least once every seven calendar
days. Storm water site inspections will include:
1. Date of the inspection.
2. Summary of the scope of the inspection.
3. Name and qualifications of the personnel making the inspection.
5. Review of erosion and sediment control measures within disturbed areas for the effectiveness in preventing impacts to receiving
waters.
6. Major observations related to the implementation of the PPP.
7. Identification of corrective actions required to maintain or modify erosion and sediment control measures.
B. Include storm water site inspection reports in the amended PPP. Incorporate any additional erosion and sediment control
measures determined as a result of the inspection. Immediately begin corrective actions on all deficiencies found within 3
calendar days of the inspection and complete within 7 calendar days following the inspection. If it is determined that making the
corrections less than 72 hours after the inspection is impracticable, it should be documented why it is impracticable and indicate
an estimated date by which the corrections will be made.
VI. NON-STORM WATER DISCHARGES
This includes subsurface drains (i.e. longitudinal and standard subdrains) and slope drains. The velocity of the discharge from
these features may be controlled by the use of headwalls or blocks, Class A stone, erosion stone or other appropriate materials.
This also includes uncontaminated groundwater from dewatering operations, which will be controlled as discussed in Section III of the
PPP.
VII. POTENTIAL SOURCES OF OFF RIGHT-OF-WAY (ROW) POLLUTION
Silts, sediment, and other forms of pollution may be transported onto highway right-of-way (ROW) as a result of a storm event.
Potential sources of pollution located outside highway ROW are beyond the control of this PPP. Pollution within highway ROW will be
conveyed and controlled per this PPP.
VIII. DEFINITIONS
A. Base PPP - Initial Pollution Prevention Plan.
B. Amended PPP - Base PPP amended during construcion. May include Plan Revisions or Contract Modifications for new items, storm water
site inspection reports, fieldbook entries made by the inspector, amended PPP site map by the Contractor, ECIP, NOI, co-permittee
certifications, and Subcontractor Request Forms. Items amending the PPP are stored electronically and are readily available upon
request.
C. Fieldbook Entries – This contains the inspector’s daily diary and bid item postings.
D. Controls - Methods, practices, or measures to minimize or prevent erosion, control sedimentation, control storm water, or minimize
contaminants from other types of waste or materials. Also called Best Management Practices (BMPs).
E. Signature Authority - Representative authorized to sign various storm water documents.
---------------------------------------------------------------------------------------------------------------------------------
CERTIFICATION STATEMENT
I certify under penalty of law that this document and all attachments were prepared under my direction or supervision in accordance
with a system designed to assure that qualified personnel properly gathered and evaluated the information submitted. Based on my inquiry
of the person or persons who manage the system, or those persons directly responsible for gathering the information, the information
submitted is, to the best of my knowledge and belief, true, accurate, and complete. I am aware that there are significant penalties for
submitting false information, including the possibility of fine and imprisonment for knowing violations.
________________________________________
Signature
________________________________________
Printed or Typed Name
________________________________________
Signature
________________________________________
Printed or Typed Name

## 110_12L (What To Update)
110-12
2020-10-20
POLLUTION PREVENTION PLAN
This project is regulated by the requirements of the Iowa Department of Natural Resources (DNR) National Pollutant Discharge Elimination
System (NPDES) General Permit No. 2 OR an Iowa Department of Natural Resources (DNR) National Pollutant Discharge Elimination System
(NPDES) individual storm water permit. The Contractor shall carry out the terms and conditions of this permit and the Pollution
Prevention Plan (PPP).
This Base PPP includes information on Roles and Responsibilities, Project Site Description, Controls, Maintenance Procedures, Inspection
Requirements, Non-Storm Water Controls, Potential Sources of Off Right-of-Way Pollution, and Definitions. This plan references other
documents rather than repeating the information contained in the documents. A copy of this Base Pollution Prevention Plan, amended as
needed during construction, will be readily available for review.
All contractors shall conduct their operations in a manner that controls pollutants, minimizes erosion, and prevents sediments from
entering waters of the state and leaving the highway right-of-way. The Contractor shall be responsible for compliance and
implementation of the PPP for their entire contract. This responsibility shall be further shared with subcontractors whose work is a
source of potential pollution as defined in this PPP.
I. ROLES AND RESPONSIBILITES
A. Designer:
1. Prepares Base PPP included in the project plan.
2. Prepares Notice of Intent (NOI) submitted to Iowa DNR.
3. Is signature authority on the Base PPP. If consultant designed, signature from Contracting Authority is also required.
B. Contractor:
1. Signs a co-permittee certification statement adhering to the requirements of the NPDES permit and this PPP. All co-permittees
are legally required under the Clean Water Act and the Iowa Administrative Code to ensure compliance with the terms and
conditions of this PPP.
2. Designates a Water Pollution Control Manager (WPCM), who has the duties and responsibilities as defined in Section 2602 of the
Standard Specifications.
3. Submits an Erosion Control Implementation Plan (ECIP) and ECIP updates according to Section 2602 of the Standard Specifications.
4. Installs and maintains appropriate controls. This work may be subcontracted as documented through Subcontractor Request Forms
(Form 830231).
5. Supervises and implements good housekeeping practices according to Paragraph III, C, 2.
6. Conducts joint required inspections of the site with inspection staff. When Contractor is not mobilized on site,
Contractor may delegate this responsibility to a trained or certified subcontractor. Contracting Authority also may waive
joint inspection requirement during winter shutdown. In both circumstances, WPCM (or trained or certified delegate from
the Contractor) is still responsible to review and sign inspection reports.
7. Complies with training and certification requirements of Section 2602 of the Standard Specifications.
8. Submits amended PPP site map according to Section 2602 of the Standard Specifications.
C. Subcontractors:
1. Sign a co-permittee certification statement adhering to the requirements of the NPDES permit and this PPP if: responsible for
sediment or erosion controls; involved in land disturbing activities; or performing work that is a source of potential pollution
as defined in this PPP. Subcontracted work items are identified in Subcontractor Request Forms (Form 830231). All
co-permittees are legally required under the Clean Water Act and the Iowa Administrative Code to ensure compliance with the
terms and conditions of this PPP.
2. Implement good housekeeping practices according to Paragraph III, C, 2.
D. RCE/Project Engineer:
1. Is Project Storm Water Manager.
2. Takes actions necessary to ensure compliance with storm water requirements including, where appropriate, issuing stop work
orders, and directing additional inspections at construction project sites that are experiencing problems with achieving permit
compliance.
3. Orders the taking of measures to cease, correct, prevent, or minimize the consequences of non-compliance with the storm water
requirements of the Applicable Permit.
4. Supervises all work necessary to meet storm water requirements at the Project, including work performed by contractors and
subcontractors.
5. Requires employees, contractors, and subcontractors to take appropriate responsive action to comply with storm water
requirements, including requiring any such person to cease or correct a violation of storm water requirements, and to order or
recommend such other actions as necessary to meet storm water requirements.
6. Is familiar with the Project PPP and storm water site map.
7. Is the point of contact for the Project for regulatory officials, Inspector, contractors, and subcontractors regarding storm
water requirements.
8. Is signature authority on Notice of Discontinuation.
9. Maintains an up-to-date record of contractors, subcontractors, and subcontracted work items through Subcontractor Request Forms
(Form 830231).
10. Makes information to determine permit compliance available to the DNR upon their request.
E. Inspector:
1. Updates PPP through fieldbook entries and storm water site inspection reports if there is a change in design, construction,
operation, or maintenance which has a significant effect on the discharge of pollutants from the project.
2. Makes information to determine permit compliance available to the DNR upon their request.
3. Conducts joint required inspections of the site with the contractor/subcontractor.
4. Completes an inspection report after each inspection.
5. Is signature authority on storm water inspection reports.
II. PROJECT SITE DESCRIPTION
A. This Pollution Prevention Plan (PPP) is for the construction of a *Describe Type of Facility*.
B. This PPP covers approximately *Provide # Of Acres* acres with an estimated *Provide # of Acres* acres being disturbed. The
portion of the PPP covered by this contract has *Provide # of Acres* acres disturbed.
C. The PPP is located in an area of *Provide # of Types Of Soil Association* soil association (*Provide Soil Association Type or*
*Types*). The estimated weighted average runoff coefficient number for this PPP after completion will be *Provide runoff
coefficient Number*.
D. Storm Water Site Map - Multiple sources of information comprise the base storm water site map including:
1. Drainage Patterns – Plan and Profile sheets and Situation plans.
2. Proposed Slopes – Cross Sections.
3. Areas of Soil Disturbance – Construction limits shown on Plan and Profile sheets.
4. Location of Structural Controls – Tabulations in C sheets.
5. Locations of Non-structural Controls – Tabulations in C sheets.
6. Locations of Stabilization Practices – Generally within construction limits shown on Plan and Profile sheets.
7. Surface Waters (including wetlands) – Project Location Map and Plan and Profile sheets.
8. Locations where Storm Water is Discharged – Plan and Profile sheets.
E. The base storm water site map is amended by contract modifications and progress payments (fieldbook entries) of completed erosion
110-12
2020-10-20
POLLUTION PREVENTION PLAN
control work. Also, due to project phasing, erosion and sediment controls shown on project plans may not be installed until
needed, based on site conditions. For example, silt fence ditch checks will typically not be installed until the ditch has been
installed. Installed locations may also be modified from tabulation locations by field staff. Installed locations will be
documented by fieldbook entries and amended PPP site map.
F. Runoff from this work will flow into *List Outlets for Runoff*.
III. CONTROLS
A. The Contractor’s ECIP specified in Article 2602.03 of the Standard Specifications for accomplishment of storm water controls should
clearly describe the intended sequence of major activities, and for each activity define the control measure and the timing during
the construction process that the measure will be implemented.
B. Preserve vegetation in areas not needed for construction.
C. Sections 2601 and 2602 of the Standard Specifications define requirements to implement erosion and sediment control measures.
Actual quantities used and installed locations may vary from the Base PPP and amendment of the plan will be documented via
fieldbook entries, amended PPP site map, or by contract modification. Additional erosion and sediment control items may be
required as determined by the inspector and/or contractor during storm water site inspections. If the work involved is not
applicable to any contract items, the work will be paid for according to Article 1109.03 paragraph B of the Standard
Specifications.
1. EROSION AND SEDIMENT CONTROLS
a. Stabilization Practices
1) Site plans will ensure that existing vegetation or natural buffers are preserved where attainable and disturbed portions
of the site will be stabilized.
2) Initialize stabilization of disturbed areas immediately after clearing, grading, excavating, or other earth disturbing
activities have:
a) Permanently ceased on any portion of the site, or
b) Temporarily ceased on any portion of the site and will not resume for a period exceeding 14 calendar days.
3) Staged permanent and/or temporary stabilizing seeding and mulching shall be completed as the disturbed areas are
completed. Incomplete areas shall be stabilized according to paragraph III, C, 1, a, 2, b above.
4) Permanent and Temporary Stabilization practices to be used for this project are located in the Estimated Project
Quantities (100-0A, 100-1A, or 100-1C) and Estimate Reference Information (100-4A) located in the C sheets. Typical
drawings detailing construction of the practices to be used on this project are referenced in the Standard Road
Plans Tabulation (105-4) in the C sheets.
5) Preservation of existing vegetation within right-of-way or easements will act as vegetative buffer strips.
6) Preservation of topsoil: Bid items to be used for this project are located in the Estimated Project Quantities (100-0A,
100-1A, or 100-1C) and Estimate Reference Information (100-4A) located in the C sheets. Additional information may be
found in Tabulations in the C or T sheets or is referenced in Section 2105 of Standard Specifications.
b. Structural Practices
1) Structural practices will be implemented to divert flows from exposed soils and detain or otherwise limit runoff and the
discharge of pollutants from exposed areas of the site. Additionally, structural practices may include: silt basins that
provide 3600 cubic feet of storage per acre drained or equivalent sediment controls, outlet structures that withdraw water
from surface when discharging basins, and controls to direct storm water to vegetated areas.
2) Structural practices to be used for this project are located in the Estimated Project Quantities (100-0A, 100-1A, or
100-1C) and Estimate Reference Information (100-4A) located in the C sheets, as well as all other item specific
Tabulations. Typical drawings detailing construction of the devices to be used on this project can be found in the B
sheets or are referenced in the Standard Road Plans Tabulation (105-4) located in the C sheets.
c. Storm Water Management
Measures shall be installed during the construction process to control pollutants in storm water discharges that will occur
after construction operations have been completed. This may include velocity dissipation devices at discharge locations and
along length of outfall channel as necessary to provide a non-erosion velocity flow from structure to water course. If
included with this project, these items are located in the Estimated Project Quantities (100-0A, 100-1A, or 100-1C) and
Estimate Reference Information (100-4A) located in the C sheets, as well as all other item specific Tabulations. Typical
drawings detailing construction of the practices to be used on this project are referenced in the Standard Road Plans
Tabulation (105-4) in the C sheets. The installation of these devices may be subject to Section 404 of the Clean Water Act.
2. OTHER CONTROLS
Contractor disposal of unused construction materials and construction material wastes shall comply with applicable state and
local waste disposal, sanitary sewer, or septic system regulations. In the event of a conflict with other governmental laws,
rules and regulations, the more restrictive applicable laws, rules or regulations shall apply.
a. Vehicle Entrances and Exits - Construct and maintain entrances and exits to prevent tracking of sediments onto roadways.
b. Material Delivery, Storage and Use - Implement practices to prevent discharge of construction materials during delivery,
storage, and use.
c. Stockpile Management - Install controls to reduce or eliminate pollution of storm water from stockpiles of soil and paving.
d. Waste Disposal - Do not discharge any materials, including building materials, into waters of the state, except as
authorized by a Section 404 permit.
e. Spill Prevention and Control - Implement chemical spill and leak prevention and response procedures to contain and clean up
spills and prevent material discharges to the storm drain system and waters of the state.
f. Concrete Residuals and Washout Wastes - Waste shall not be discharged to a surface water and is not allowed to adversely
affect a water of the state. Designate temporary concrete washout facilities for rinsing out concrete trucks. Provide
directions to truck drivers where designated washout facilities are located. Designated washout areas should be
located at least 50 feet away from storm drains, streams or other water bodies. Care should be taken to ensure these
facilities do not overflow during storm events.
g. Concrete Grooving/Grinding Slurry – Do not discharge slurry to a waterbody or storm drain. Slurry may be applied on
foreslopes or removed from the project.
h. Vehicle and Equipment Storage and Maintenance Areas - Perform on site fueling and maintenance in accordance with all
environment laws such as proper storage of onsite fuels and proper disposal of used engine oil or other fluids on site.
Employ washing practices that prevent contamination of surface and ground water from wash water. Wash waters must be
treated in a sediment basin or alternative control that provides equivalent or better treatment prior to discharge.
i. Litter Management - Ensure employees properly dispose of litter. Minimize exposure of trash if exposure to precipitation or
storm water would result in a discharge of pollutants.
j. Dewatering – Properly treat water to remove suspended sediment before it re-enters a waterbody or discharges off-site.
Measures are also to be taken to prevent scour erosion at dewatering discharge point.
3. APPROVED STATE OR LOCAL PLANS
During the course of this construction, it is possible that situations will arise where unknown materials will be encountered.
When such situations are encountered, they will be handled according to all federal, state, and local regulations in effect at
the time.
IV. MAINTENANCE PROCEDURES
The Contractor is required to maintain all temporary erosion and sediment control measures in proper working order, including
110-12
2020-10-20
POLLUTION PREVENTION PLAN
cleaning, repairing, or replacing them throughout the contract period. This shall begin when the features have lost 50% of their
capacity.
V. INSPECTION REQUIREMENTS
A. Inspections shall be made jointly by the Contractor and the Contracting Authority's inspector at least once every seven calendar
days. Storm water site inspections will include:
1. Date of the inspection.
2. Summary of the scope of the inspection.
3. Name and qualifications of the personnel making the inspection.
5. Review of erosion and sediment control measures within disturbed areas for the effectiveness in preventing impacts to receiving
waters.
6. Major observations related to the implementation of the PPP.
7. Identification of corrective actions required to maintain or modify erosion and sediment control measures.
B. Include storm water site inspection reports in the amended PPP. Incorporate any additional erosion and sediment control
measures determined as a result of the inspection. Immediately begin corrective actions on all deficiencies found within 3
calendar days of the inspection and complete within 7 calendar days following the inspection. If it is determined that making the
corrections less than 72 hours after the inspection is impracticable, it should be documented why it is impracticable and indicate
an estimated date by which the corrections will be made.
VI. NON-STORM WATER DISCHARGES
This includes subsurface drains (i.e. longitudinal and standard subdrains) and slope drains. The velocity of the discharge from
these features may be controlled by the use of headwalls or blocks, Class A stone, erosion stone or other appropriate materials.
This also includes uncontaminated groundwater from dewatering operations, which will be controlled as discussed in Section III of the
PPP.
VII. POTENTIAL SOURCES OF OFF RIGHT-OF-WAY (ROW) POLLUTION
Silts, sediment, and other forms of pollution may be transported onto highway right-of-way (ROW) as a result of a storm event.
Potential sources of pollution located outside highway ROW are beyond the control of this PPP. Pollution within highway ROW will be
conveyed and controlled per this PPP.
VIII. DEFINITIONS
A. Base PPP - Initial Pollution Prevention Plan.
B. Amended PPP - Base PPP amended during construcion. May include Plan Revisions or Contract Modifications for new items, storm water
site inspection reports, fieldbook entries made by the inspector, amended PPP site map by the Contractor, ECIP, NOI, co-permittee
certifications, and Subcontractor Request Forms. Items amending the PPP are stored electronically and are readily available upon
request.
C. Fieldbook Entries – This contains the inspector’s daily diary and bid item postings.
D. Controls - Methods, practices, or measures to minimize or prevent erosion, control sedimentation, control storm water, or minimize
contaminants from other types of waste or materials. Also called Best Management Practices (BMPs).
E. Signature Authority - Representative authorized to sign various storm water documents.
---------------------------------------------------------------------------------------------------------------------------------
CERTIFICATION STATEMENT
I certify under penalty of law that this document and all attachments were prepared under my direction or supervision in accordance
with a system designed to assure that qualified personnel properly gathered and evaluated the information submitted. Based on my inquiry
of the person or persons who manage the system, or those persons directly responsible for gathering the information, the information
submitted is, to the best of my knowledge and belief, true, accurate, and complete. I am aware that there are significant penalties for
submitting false information, including the possibility of fine and imprisonment for knowing violations.
________________________________________
Signature
________________________________________
Printed or Typed Name
________________________________________
Signature
________________________________________
Printed or Typed Name