## PPCBeamDataSheet1
PPC Beam Data Spreadsheet |  |  |  | Version 1.4 |  | Last Revised on 11-23-2015
Project No. | BRFN-151-4(126)--39-53 |  |  | Notes: | Beam Bearing Assembly Height is the total height of the bearing assembly excluding any components embedded in the beam.
Design No. | 124 |  |  |  | Bridge Designer to fill in gray cells and set up spreadsheet to match plan set.
County | Jones |  |  | * | Bridge Contractor to document individual beam identification number as installed on the bridge.
Other Info. |  |  |  | ** | Central Construction and Materials to document the initial and final actual beam cambers for each beam installed.
|  |  |  | *** | Bridge Contractor to document as constructed (actual) beam seat elevation at each substructure unit for each beam line.
BEAM INFORMATION
|  |  | Design Camber |  | ** Actual Camber |  | Beam Bearing Assembly Height |  | Beam Seat Elevation: From Plan |  | *** Beam Seat Elevation: Measured
|  | * Beam | Initial | Final | Initial | Final | S Abut. | N Abut. | S Abut. | N Abut. | S Abut. | N Abut.
Beam | Beam Size | Number (BN) | (in) | (in) | (in) | (in) | (in) | (in)
1 | BTC120 |  | 4.48 | 7.17 |  |  | 3" - 3 x 3 BAR | 3" - 3 x 3 BAR | 844.465 | 844.1602
2 | BTC120 |  | 4.48 | 7.17 |  |  | 3" - 3 x 3 BAR | 3" - 3 x 3 BAR | 844.6032 | 844.2984
3 | BTC120 |  | 4.48 | 7.17 |  |  | 3" - 3 x 3 BAR | 3" - 3 x 3 BAR | 844.7415 | 844.4367
4 | BTC120 |  | 4.48 | 7.17 |  |  | 3" - 3 x 3 BAR | 3" - 3 x 3 BAR | 844.8068 | 844.502
5 | BTC120 |  | 4.48 | 7.17 |  |  | 3" - 3 x 3 BAR | 3" - 3 x 3 BAR | 844.6638 | 844.359
6 | BTC120 |  | 4.48 | 7.17 |  |  | 3" - 3 x 3 BAR | 3" - 3 x 3 BAR | 844.5103 | 844.2055

## PPCBeamDataSheet2
| Note: | Bridge Designer shall adjust figure below as necessary to match the let bridge plans.
Drawing not to scale.
|  | C.L. S ABUT. BRG. |  | C.L. N ABUT. BRG.
1
BEAM LINE A
2
BEAM LINE B
3
BEAM LINE C
4
BEAM LINE D
5
BEAM LINE E
6
BEAM LINE F