## PPCBeamDataSheet1
PPC Beam Data Spreadsheet |  |  |  | Version 1.4 |  | Last Revised on 11-23-2015
Project No. | BRFN-063-1(94)--39-26 |  |  | Notes: | Beam Bearing Assembly Height is the total height of the bearing assembly excluding any components embedded in the beam.
Design No. | 225 |  |  |  | Bridge Designer to fill in gray cells and set up spreadsheet to match plan set.
County | DAVIS |  |  | * | Bridge Contractor to document individual beam identification number as installed on the bridge.
Other Info. |  |  |  | ** | Central Construction and Materials to document the initial and final actual beam cambers for each beam installed.
|  |  |  | *** | Bridge Contractor to document as constructed (actual) beam seat elevation at each substructure unit for each beam line.
BEAM INFORMATION
|  |  | Design Camber |  | ** Actual Camber |  | Beam Bearing Assembly Height |  |  |  | Beam Seat Elevation: From Plan |  |  |  | *** Beam Seat Elevation: Measured
|  | * Beam | Initial | Final | Initial | Final | S Abut. | Pier #1 | Pier #2 | N Abut. | S Abut. | Pier #1 | Pier #2 | N Abut. | S Abut. | Pier #1 | Pier #2 | N Abut.
Beam | Beam Size | Number (BN) | (in) | (in) | (in) | (in) | (in) | (in) | (in) | (in)
1 | B50 |  | 0.67 | 1.24 |  |  | 3" - 3 x 3 BAR | 1" - PLAIN NEOPRENE |  |  | 782.3525 | 783.0586
2 | B50 |  | 0.67 | 1.24 |  |  | 3" - 3 x 3 BAR | 1" - PLAIN NEOPRENE |  |  | 782.4721 | 783.1699
3 | B50 |  | 0.67 | 1.24 |  |  | 3" - 3 x 3 BAR | 1" - PLAIN NEOPRENE |  |  | 782.5921 | 783.2814
4 | B50 |  | 0.67 | 1.24 |  |  | 3" - 3 x 3 BAR | 1" - PLAIN NEOPRENE |  |  | 782.6823 | 783.3632
5 | B50 |  | 0.67 | 1.24 |  |  | 3" - 3 x 3 BAR | 1" - PLAIN NEOPRENE |  |  | 782.5595 | 783.232
6 | B50 |  | 0.67 | 1.24 |  |  | 3" - 3 x 3 BAR | 1" - PLAIN NEOPRENE |  |  | 782.4071 | 783.0711
7 | B50 |  | 0.67 | 1.24 |  |  | 3" - 3 x 3 BAR | 1" - PLAIN NEOPRENE |  |  | 782.2549 | 782.9105
8 | B67 |  | 1.69 | 2.98 |  |  |  | 1" - PLAIN NEOPRENE | 1" - PLAIN NEOPRENE |  |  | 783.0586 | 784.2347
9 | B67 |  | 1.69 | 2.98 |  |  |  | 1" - PLAIN NEOPRENE | 1" - PLAIN NEOPRENE |  |  | 783.1699 | 784.3347
10 | B67 |  | 1.69 | 2.98 |  |  |  | 1" - PLAIN NEOPRENE | 1" - PLAIN NEOPRENE |  |  | 783.2814 | 784.435
11 | B67 |  | 1.69 | 2.98 |  |  |  | 1" - PLAIN NEOPRENE | 1" - PLAIN NEOPRENE |  |  | 783.3632 | 784.5056
12 | B67 |  | 1.69 | 2.98 |  |  |  | 1" - PLAIN NEOPRENE | 1" - PLAIN NEOPRENE |  |  | 783.232 | 784.3631
13 | B67 |  | 1.69 | 2.98 |  |  |  | 1" - PLAIN NEOPRENE | 1" - PLAIN NEOPRENE |  |  | 783.0711 | 784.1909
14 | B67 |  | 1.69 | 2.98 |  |  |  | 1" - PLAIN NEOPRENE | 1" - PLAIN NEOPRENE |  |  | 782.9105 | 784.0191
15 | B50 |  | 0.67 | 1.24 |  |  |  |  | 1" - PLAIN NEOPRENE | 3" - 3 x 3 BAR |  |  | 784.2347 | 785.2975
16 | B50 |  | 0.67 | 1.24 |  |  |  |  | 1" - PLAIN NEOPRENE | 3" - 3 x 3 BAR |  |  | 784.3347 | 785.389
17 | B50 |  | 0.67 | 1.24 |  |  |  |  | 1" - PLAIN NEOPRENE | 3" - 3 x 3 BAR |  |  | 784.435 | 785.4809
18 | B50 |  | 0.67 | 1.24 |  |  |  |  | 1" - PLAIN NEOPRENE | 3" - 3 x 3 BAR |  |  | 784.5056 | 785.543
19 | B50 |  | 0.67 | 1.24 |  |  |  |  | 1" - PLAIN NEOPRENE | 3" - 3 x 3 BAR |  |  | 784.3631 | 785.3922
20 | B50 |  | 0.67 | 1.24 |  |  |  |  | 1" - PLAIN NEOPRENE | 3" - 3 x 3 BAR |  |  | 784.1909 | 785.2116
21 | B50 |  | 0.67 | 1.24 |  |  |  |  | 1" - PLAIN NEOPRENE | 3" - 3 x 3 BAR |  |  | 784.0191 | 785.0313