## Jackson 325
Sheet List
|  |  | Project: | Jackson 325
|  |  | DOT: | Iowa DOT | [5 empty] | ES
5% - The drawing model is created with no more than a sheet name and blank border. | [9 empty] | TJJ
50% - The general layout or standard sheet is drafted with known dimensions. Most remaining work could be marked up on sheet by Designer. | [9 empty] | AR
70% - Designer completes design & drawings and sheet is ready to be checked by reviewer.
70% to 80% - A portion of but not all of the drawings or design calculations have been reviewed.
80% - Checker has completed at least 1 round of review on all aspects of design and drawings.
80% to 90% - A portion of but not all of the Checker comments have been implemented after concurrence with Designer.
90% - Designer and Checker have reached concurrence and implemented all review comments and DOCUMENTED them in designated folder. - Ready for QA
95% - QA has been completed and any comments have been incorporated. IADOT comments are pending.
95% to 100% - IADOT submittal review comment incorporation and checking.
100% - Ready for Bid / Contracts Turn-In. | [6 empty] | Completion Check = | 90%
List of Drawings | [6 empty] | Avg. Complete = | 100%
Design Sheet No. | V SHEETS | Total Sheets | Drawing Title | Created | Designer | Check | QA | % Complete | Comments
|  | 1 | Title Sheet | ES | ES | TJJ |  | 100%
|  | 2 | Map Sheet | ES | ES | TJJ |  | 100%
1 | 1 | 3 | Estimated Quantities #325 | ES | ES | TJJ |  | 100%
2 | 2 | 4 | General Notes #325 | ES | ES | TJJ |  | 100%
3 | 3 | 5 | Situation Plan #325 | ES | ES | TJJ |  | 100%
4 | 4 | 6 | Stage Details #325 | ES | ES | TJJ |  | 100%
5 | 5 | 7 | Abutment & Barrier Removal Details #325 | ES | ES | TJJ |  | 100%
6 | 6 | 8 | Abutment & Barrier Repair Details #325 | ES | ES | TJJ |  | 100%
7 | 7 | 9 | Abutment & Barrier Details #325 | ES | ES | TJJ |  | 100% | Includes Rebar Table
8 | 8 | 10 | Expansion Device Details 1026s1 #325 | ES | ES | TJJ |  | 100% | STANDARD 1026s1 - Modified barrier section to look like the existing one
9 | 9 | 11 | Expansion Device Details 1026s2 #325 | ES | ES | TJJ |  | 100% | STANDARD 1026s2