## PPCBeamDataSheet1
PPC Beam Data Spreadsheet |  |  |  | Version 1.4 |  | Last Revised on 11-23-2015
Project No. | BRFN-063-1(94)--39-26 |  |  | Notes: | Beam Bearing Assembly Height is the total height of the bearing assembly excluding any components embedded in the beam.
Design No. | 225 |  |  |  | Bridge Designer to fill in gray cells and set up spreadsheet to match plan set.
County | DAVIS |  |  | * | Bridge Contractor to document individual beam identification number as installed on the bridge.
Other Info. |  |  |  | ** | Central Construction and Materials to document the initial and final actual beam cambers for each beam installed.
|  |  |  | *** | Bridge Contractor to document as constructed (actual) beam seat elevation at each substructure unit for each beam line.
BEAM INFORMATION
|  |  | Design Camber |  | ** Actual Camber |  | Beam Bearing Assembly Height |  |  |  | Beam Seat Elevation: From Plan |  |  |  | *** Beam Seat Elevation: Measured
|  | * Beam | Initial | Final | Initial | Final | S Abut. | Pier #1 | Pier #2 | N Abut. | S Abut. | Pier #1 | Pier #2 | N Abut. | S Abut. | Pier #1 | Pier #2 | N Abut.
Beam | Beam Size | Number (BN) | (in) | (in) | (in) | (in) | (in) | (in) | (in) | (in)
1 | B50 |  | 0.55 | 1.02 |  |  | 3" - 3 x 3 BAR | 1" - PLAIN NEOPRENE |  |  | 782.3525 | 783.0795
2 | B50 |  | 0.55 | 1.02 |  |  | 3" - 3 x 3 BAR | 1" - PLAIN NEOPRENE |  |  | 782.4721 | 783.1907
3 | B50 |  | 0.55 | 1.02 |  |  | 3" - 3 x 3 BAR | 1" - PLAIN NEOPRENE |  |  | 782.5921 | 783.3022
4 | B50 |  | 0.55 | 1.02 |  |  | 3" - 3 x 3 BAR | 1" - PLAIN NEOPRENE |  |  | 782.6823 | 783.3841
5 | B50 |  | 0.55 | 1.02 |  |  | 3" - 3 x 3 BAR | 1" - PLAIN NEOPRENE |  |  | 782.5595 | 783.2529
6 | B50 |  | 0.55 | 1.02 |  |  | 3" - 3 x 3 BAR | 1" - PLAIN NEOPRENE |  |  | 782.4071 | 783.092
7 | B50 |  | 0.55 | 1.02 |  |  | 3" - 3 x 3 BAR | 1" - PLAIN NEOPRENE |  |  | 782.2549 | 782.9314
8 | B67 |  | 1.43 | 2.65 |  |  |  | 1" - PLAIN NEOPRENE | 1" - PLAIN NEOPRENE |  |  | 783.0795 | 784.2556
9 | B67 |  | 1.43 | 2.65 |  |  |  | 1" - PLAIN NEOPRENE | 1" - PLAIN NEOPRENE |  |  | 783.1907 | 784.3556
10 | B67 |  | 1.43 | 2.65 |  |  |  | 1" - PLAIN NEOPRENE | 1" - PLAIN NEOPRENE |  |  | 783.3022 | 784.4558
11 | B67 |  | 1.43 | 2.65 |  |  |  | 1" - PLAIN NEOPRENE | 1" - PLAIN NEOPRENE |  |  | 783.3841 | 784.5264
12 | B67 |  | 1.43 | 2.65 |  |  |  | 1" - PLAIN NEOPRENE | 1" - PLAIN NEOPRENE |  |  | 783.2529 | 784.3839
13 | B67 |  | 1.43 | 2.65 |  |  |  | 1" - PLAIN NEOPRENE | 1" - PLAIN NEOPRENE |  |  | 783.092 | 784.2118
14 | B67 |  | 1.43 | 2.65 |  |  |  | 1" - PLAIN NEOPRENE | 1" - PLAIN NEOPRENE |  |  | 782.9314 | 784.0399
15 | B50 |  | 0.55 | 1.02 |  |  |  |  | 1" - PLAIN NEOPRENE | 3" - 3 x 3 BAR |  |  | 784.2556 | 785.2975
16 | B50 |  | 0.55 | 1.02 |  |  |  |  | 1" - PLAIN NEOPRENE | 3" - 3 x 3 BAR |  |  | 784.3556 | 785.389
17 | B50 |  | 0.55 | 1.02 |  |  |  |  | 1" - PLAIN NEOPRENE | 3" - 3 x 3 BAR |  |  | 784.4558 | 785.4809
18 | B50 |  | 0.55 | 1.02 |  |  |  |  | 1" - PLAIN NEOPRENE | 3" - 3 x 3 BAR |  |  | 784.5264 | 785.543
19 | B50 |  | 0.55 | 1.02 |  |  |  |  | 1" - PLAIN NEOPRENE | 3" - 3 x 3 BAR |  |  | 784.3839 | 785.3922
20 | B50 |  | 0.55 | 1.02 |  |  |  |  | 1" - PLAIN NEOPRENE | 3" - 3 x 3 BAR |  |  | 784.2118 | 785.2116
21 | B50 |  | 0.55 | 1.02 |  |  |  |  | 1" - PLAIN NEOPRENE | 3" - 3 x 3 BAR |  |  | 784.0399 | 785.0313